## Overview
metric | value
project | Week 6 Unibo Dataset Validation
generated_at | 2026-07-04T23:09:56
final_manual_labels | 432
scanpoint_frames | 72
manual_labels_per_frame | 6
yolov8s_primary_bboxes | 540
medium_high_marker_candidates | 196
recommended_split_v2_train_labels | 288
recommended_split_v2_val_labels | 72
recommended_split_v2_test_labels | 72
preliminary_segmentation_records | 540
final_package_v1_missing_files | 0
current_goal | Close all task-sheet gaps and build final package v2.

## Task Compliance
task_id | priority | requirement | status | current_assessment | evidence | next_action
Task 6 | core | Test at least one segmentation approach and evaluate whether segmentation improves shape/posture/colour-marker/ROI/contact estimation. | done | No clear preliminary segmentation output found in Week 6 outputs. Need at least a baseline segmentation test or documented fallback. Preliminary bbox-guided segmentation baseline has been implemented with 540 segmentation records and 72 overlay images. | segmentation_candidates=none found | Include preliminary segmentation outputs in final package v2.
Deliverable 7 | deliverable | Preliminary segmentation results. | done | No clear segmentation output yet. Preliminary segmentation CSV/JSON, quality summaries, overlays, and contact sheet have been generated. | no required output found yet | Include preliminary segmentation outputs in final package v2.
Deliverable 8 | deliverable | Updated shared Excel file with tasks, experiments, outputs, and issues. | done | No Excel tracker found. Updated shared Excel/task tracker has been generated. | no required output found yet | Include tracker XLSX in final package v2.
Task 2 | core | Extract labels from all GT files and create unified table/JSON with video_id, crate_id, camera_id, frame_index, timestamp, pig_id/colour_id, bbox, behaviour_label, label_source. | done | Recommended CSV exists and preserves 432 manual labels. Recommended JSON is not yet generated. BBox fields in GT are not manual bbox ground truth; detector bbox table exists separately. Recommended GT JSON, schema JSON, nested viewer JSON, and camera/pen/crate/video summary have been generated. | exists: outputs/unified_ground_truth/week6_unified_ground_truth_v2_with_recommended_split_v2.csv (432 rows) ¦ missing: outputs/unified_ground_truth/week6_unified_ground_truth_v2_with_recommended_split_v2.json ¦ exists: outputs/unified_ground_truth/week6_unified_ground_truth_v2_with_recovered_videos.json ¦ exists: outputs/feature_extractors/week6_yolov8s_all_scanpoint_detections_with_qc_flags.csv (540 rows) | Include new JSON/schema outputs in final package v2.
Task 4 | core | Visualization interface that loads Unibo video and associated JSON annotation; displays bbox, pig colour/ID, behaviour label, timestamp/frame. | done | Overlay videos and images exist, but a minimal reusable interface/script that loads video + JSON annotation is not yet clearly packaged. Streamlit app and static HTML visualization viewer have been generated. | exists: outputs/visual_label_check/marker_bbox_overlay_v3_video/week6_marker_bbox_overlay_v3_slideshow.mp4 ¦ exists: outputs/visual_label_check/bbox_count_warning_qc/all_bbox_count_warning_frames_contact_sheet.jpg ¦ interface_candidates= | Include interface_demo directory in final package v2.
Task 5 | core | Test different feature extractors: trajectory, ROI/resource, group-spatial, YOLO detector embeddings, crop-based embeddings; optional DINOv2/VideoMAE/keypoints. | done | Implemented: bbox geometry/QC, conservative bbox subset, crop colour-marker features, candidate colour association, comparison table. Missing or only conceptual: trajectory features, ROI/resource features, group-spatial features, YOLO detector embeddings, crop-based embeddings. Additional lightweight feature extractor tables have been generated: bbox geometry, group-spatial, coarse ROI/resource proxy, crop descriptors, and trajectory feasibility. | exists: outputs/feature_extractors/week6_yolov8s_all_scanpoint_detections_with_qc_flags.csv (540 rows) ¦ exists: outputs/feature_extractors/week6_yolov8s_conservative_detections_score_ge_0_50.csv (447 rows) ¦ exists: outputs/feature_extractors/week6_crop_colour_marker_features.csv (540 rows) ¦ exists: outputs/feature_extractors/week6_candidate_bbox_to_colour_assignments.csv (196 rows) ¦ exists: outputs/feature_extractors/week6_feature_extractor_comparison_final_clean_v3.csv (8 rows) ¦ exists: outputs/feature_extractors/week6_feature_extractor_recommendations_final_clean_v3.csv (5 rows) | Include lightweight feature extractor outputs in final package v2.
Deliverable 2 | deliverable | Unified GT extraction table/JSON. | done | CSV exists; recommended JSON missing. Recommended GT JSON has been generated. | exists: outputs/unified_ground_truth/week6_unified_ground_truth_v2_with_recommended_split_v2.csv (432 rows) ¦ missing: outputs/unified_ground_truth/week6_unified_ground_truth_v2_with_recommended_split_v2.json | Include CSV and JSON in final package v2.
Task 1 | core | Unibo dataset analysis: videos, cameras, pens/crates, scan windows, annotated frames, pigs, behaviour distribution, rare/missing labels. | done | Dataset statistics are mostly complete. Need one extra dedicated crate/pen/camera summary table to make the task sheet mapping explicit. | exists: outputs/dataset_statistics/week6_final_dataset_overview_metrics.csv (27 rows) ¦ exists: outputs/dataset_statistics/week6_final_behaviour_distribution.csv (11 rows) ¦ exists: outputs/dataset_statistics/week6_final_rare_behaviour_classes.csv (4 rows) ¦ exists: outputs/dataset_statistics/week6_final_hourly_annotation_distribution.csv (12 rows) ¦ exists: outputs/dataset_statistics/week6_final_colour_distribution.csv (6 rows) | Create final crate/pen/camera/video summary table and add it to v2 package.
Task 3 | core | Dataset splitting protocol that avoids leakage and represents behaviours when possible. | done | Recommended split v2 is complete: train/val/test at video-hour level, no leakage, improved behaviour coverage. | exists: outputs/dataset_statistics/week6_recommended_split_v2_summary.csv (3 rows) ¦ exists: outputs/dataset_statistics/week6_recommended_split_v2_video_level.csv (12 rows) ¦ exists: outputs/dataset_statistics/week6_recommended_split_v2_behaviour_coverage.csv (3 rows) ¦ exists: outputs/dataset_statistics/week6_postfix_final_consistency_audit.csv (16 rows) | No major action. Include split protocol in final report/package v2.
Deliverable 1 | deliverable | Unibo dataset statistics report. | done | Already covered by dataset statistics and final outline. | exists: outputs/dataset_statistics/week6_final_dataset_overview_metrics.csv (27 rows) ¦ exists: outputs/dataset_statistics/week6_final_behaviour_distribution.csv (11 rows) ¦ exists: outputs/dataset_statistics/week6_final_rare_behaviour_classes.csv (4 rows) | No major action.
Deliverable 3 | deliverable | Proposed train/test split protocol. | done | Recommended split v2 exists. | exists: outputs/dataset_statistics/week6_recommended_split_v2_summary.csv (3 rows) ¦ exists: outputs/dataset_statistics/week6_recommended_split_v2_video_level.csv (12 rows) ¦ exists: outputs/dataset_statistics/week6_recommended_split_v2_behaviour_coverage.csv (3 rows) | No major action.
Deliverable 4 | deliverable | Visualization interface demo. | done | Video demo exists; reusable interface file not yet packaged. Reusable Streamlit and static HTML viewer artifacts have been generated. | exists: outputs/visual_label_check/marker_bbox_overlay_v3_video/week6_marker_bbox_overlay_v3_slideshow.mp4 | Include interface demo in final package v2.
Deliverable 5 | deliverable | Screenshots/videos showing bbox + pig colour + behaviour label. | done | Visualization video and QC contact sheets exist. | exists: outputs/visual_label_check/marker_bbox_overlay_v3_video/week6_marker_bbox_overlay_v3_slideshow.mp4 ¦ exists: outputs/visual_label_check/bbox_count_warning_qc/all_bbox_count_warning_frames_contact_sheet.jpg | No major action.
Deliverable 6 | deliverable | Feature extractor comparison. | done | Comparison table exists, but implementations can be expanded. | exists: outputs/feature_extractors/week6_feature_extractor_comparison_final_clean_v3.csv (8 rows) ¦ exists: outputs/feature_extractors/week6_feature_extractor_recommendations_final_clean_v3.csv (5 rows) | Add extra lightweight feature tables.

## Experiments
experiment_id | experiment | status | primary_output | records_or_count | notes
E01 | Raw Unibo video inventory | completed | outputs/dataset_statistics/week6_final_dataset_overview_metrics.csv | 84 raw work videos | Raw videos and naming/camera metadata analyzed.
E02 | Excel annotation parsing | completed | outputs/unified_ground_truth/week6_unified_ground_truth_v2_with_recommended_split_v2.csv | 432 labels | Manual scan-sampling labels parsed and linked to videos.
E03 | Recommended GT JSON/schema | completed | outputs/unified_ground_truth/week6_unified_ground_truth_v2_with_recommended_split_v2.json | 432 records | JSON, schema, nested viewer JSON, and metadata summary generated.
E04 | Scanpoint frame extraction | completed | outputs/unified_ground_truth/week6_scanpoint_frame_index.csv | 72 frames | Each scanpoint frame links to six manual labels.
E05 | YOLOv8-s bbox detection | completed | outputs/feature_extractors/week6_yolov8s_all_scanpoint_detections_with_qc_flags.csv | 540 bboxes | Automatic detector bboxes with QC flags.
E06 | Crop colour-marker features | completed | outputs/feature_extractors/week6_crop_colour_marker_features.csv | 540 crops, 196 medium/high candidates | Candidate-level identity/colour evidence only.
E07 | Recommended split v2 | completed | outputs/dataset_statistics/week6_recommended_split_v2_summary.csv | 288/72/72 labels | Video-hour no-leakage split.
E08 | Visualization interface demo | completed | interface_demo/week6_visualization_streamlit_app.py | 72 frames / 432 labels / 540 bboxes | Streamlit and static HTML viewer generated.
E09 | Lightweight feature extractor tests | completed | outputs/dataset_statistics/week6_lightweight_feature_extractor_test_summary.csv | bbox/group/ROI/crop/trajectory tables | Task 5 expanded beyond detector/marker features.
E10 | Preliminary segmentation baseline | completed | outputs/feature_extractors/week6_preliminary_bbox_guided_segmentation_features.csv | 540 segmentation records | GrabCut + Otsu fallback; not manual segmentation GT.
E11 | Final package v1 | completed | final_delivery_package/Week6_Unibo_Dataset_Validation_Final_Package.zip | 29 files, 0 missing | Zip and checksum verified; v2 will include additional task-sheet outputs.

## Key Outputs
path | exists | size_mb | type | package_v2_include
outputs/unified_ground_truth/week6_unified_ground_truth_v2_with_recommended_split_v2.csv | TRUE | 0.419 | csv | yes
outputs/unified_ground_truth/week6_unified_ground_truth_v2_with_recommended_split_v2.json | TRUE | 0.863 | json | yes
outputs/unified_ground_truth/week6_unified_ground_truth_v2_with_recommended_split_v2_schema.json | TRUE | 0.008 | json | yes
outputs/unified_ground_truth/week6_scanpoint_annotations_nested_for_viewer.json | TRUE | 0.41 | json | yes
outputs/dataset_statistics/week6_camera_pen_crate_video_summary.csv | TRUE | 0.002 | csv | yes
interface_demo/week6_visualization_streamlit_app.py | TRUE | 0.002 | py | yes
interface_demo/week6_static_visualization_viewer.html | TRUE | 0.036 | html | yes
outputs/feature_extractors/week6_bbox_geometry_features.csv | TRUE | 0.22 | csv | yes
outputs/feature_extractors/week6_group_spatial_features_per_frame.csv | TRUE | 0.023 | csv | yes
outputs/feature_extractors/week6_coarse_roi_resource_proxy_features.csv | TRUE | 0.141 | csv | yes
outputs/feature_extractors/week6_crop_descriptor_baseline_features.csv | TRUE | 0.137 | csv | yes
outputs/feature_extractors/week6_crop_descriptor_plus_marker_features.csv | TRUE | 0.176 | csv | yes
outputs/feature_extractors/week6_trajectory_feature_feasibility_report.csv | TRUE | 0.001 | csv | yes
outputs/feature_extractors/week6_preliminary_bbox_guided_segmentation_features.csv | TRUE | 0.262 | csv | yes
outputs/feature_extractors/week6_preliminary_bbox_guided_segmentation_features.json | TRUE | 0.62 | json | yes
outputs/feature_extractors/week6_preliminary_segmentation_frame_summary.csv | TRUE | 0.012 | csv | yes
outputs/dataset_statistics/week6_preliminary_segmentation_quality_summary.csv | TRUE | 0.001 | csv | yes
outputs/dataset_statistics/week6_preliminary_segmentation_status_summary.csv | TRUE | 0 | csv | yes
outputs/visual_label_check/week6_preliminary_segmentation_contact_sheet.jpg | TRUE | 1.073 | jpg | yes
outputs/visual_label_check/marker_bbox_overlay_v3_video/week6_marker_bbox_overlay_v3_slideshow.mp4 | TRUE | 6.764 | mp4 | yes

## Issues Limitations
issue_id | category | severity | status | issue | mitigation
L01 | annotation_scope | medium | documented | Labels come from one Excel sheet/day/camera-pen context. | Clearly report scope and avoid over-generalizing results.
L02 | video_linkage | medium | documented | 15:00-19:00 c-token video mappings are candidate recovered mappings. | Keep video_mapping_confidence as medium_needs_visual_confirmation.
L03 | bbox_ground_truth | medium | documented | Bboxes are automatic detector outputs, not manual bbox annotations. | Keep detector bboxes in feature extractor tables and separate from manual GT labels.
L04 | identity | high | documented | BBox-to-colour identity is candidate-level only. | Use marker assignments for QC/candidate analysis, not final identity-resolved GT.
L05 | marker_colour | medium | documented | Red markers are ambiguous between red_neck and red_tail. | Do not claim final red_neck/red_tail assignment from red marker alone.
L06 | segmentation | medium | documented | Preliminary segmentation masks are automatic and not manual segmentation GT. | Use as exploratory shape/posture features only; validate manually before label claims.
L07 | trajectory | high | documented | Stable identity-resolved tracking is not validated. | Do not claim final per-pig trajectory features; document feasibility only.
L08 | class_balance | medium | documented | Rare behaviour classes remain limited. | Use careful evaluation, avoid overclaiming performance on rare classes.

## Next Steps
step_id | priority | status | task | expected_output
N01 | high | next | Re-run compliance audit after new outputs. | updated compliance matrix with all required deliverables done.
N02 | high | next | Build final package v2 including JSON, interface, extra features, segmentation, tracker. | Final_Package_v2.zip
N03 | high | next | Run zip integrity and checksum verification for final package v2. | No errors and all checksums OK.
N04 | medium | future | Manually inspect segmentation overlays and mark low-quality masks. | segmentation visual QC table.
N05 | medium | future | Add validated tracker/identity association if needed. | identity-resolved trajectory features.